## Goals
Id | Description | Comments | Due | Started | Finished | Added | Current Period: 4
1 | Install JabRef on my personal machine |  | 2016-05-18 | 2 | 2 | 1
2 | Regain access to my UVA online account |  | 2016-05-18 | 2 | 2 | 1
3 | Get set up in my Campus Office |  | 2016-05-18 | 2 | 2 | 1
4 | Clone literature repository |  | 2016-05-19 | 2 | 2 | 1 |  | Which week do I plan on completing a task?
5 | Set up my PTL Private Repository |  | 2016-05-19 | 2 | 2 | 1 |  | Which week do I plan on starting to work on a task?
6 | Write my first weekly update to my Repository |  | 2016-05-19 | 2 | 2 | 1
8 | Read Prof. Gerber's Thoughts |  | 2016-05-25 | 2 | 3 | 2 |  | If I worked on it in a week show in last week
9 | Connect to Campus Wifi |  | 2016-05-25 | 3 | 3 | 3 |  | If I showed it in last week but didn't finish show in next week
7 | Create Linux instance on AWS with R installed |  | 2016-05-25 | 3 | 3 | 2
10 | Create curriculum plan |  | 2016-06-01 | 2 | 3 | 2 |  | Last Week -- everything I worked on
11 | Create publication plan |  | 2016-06-01 | 2 | 3 | 2 |  | Next Week -- whatever I choose to put here
12 | Create thesis plan |  | 2016-06-01 | 2 | 3 | 2
23 | Create Task Spreadsheet |  | 2016-06-01 | 3 | 3 | 3
15 | Determine Pace for Article Survey |  | 2016-06-01 | 3 | 3 | 3
13 | Introduction to Statistical Learning Chp 2 |  | 2016-06-08 | 3 |  | 3
14 | Reinforcement Learning an Introduction |  | 2016-06-08 | 3 |  | 3
24 | Read all article Abstracts |  | 2016-06-08 | 4 |  | 4
25 | Add hours to Update Sheet |  | 2016-06-08 | 4 | 4 | 4
26 | Account for Conferences In Pub Plan |  | 2016-06-08 | 4 |  | 4
27 | Finish a complete class plan |  | 2016-06-08 | 4 |  | 4
16 | Present A Survey Of My Summer Reading |  | 2016-07-26 |  |  | 3
17 | Fill out my vaccine medical form | Dr. Matt Hipke | 2016-08-01 |  |  | 3
18 | Sign up as TA |  | 2016-08-01 |  |  | 3
19 | Get campus ID card |  | 2016-08-01 |  |  | 3
20 | Get campus parking pass |  | 2016-08-01 |  |  | 3
21 | Get in touch with Human Resources about TA |  | 2016-08-01 |  |  | 3
22 | Research journals and submission criteria |  | 2016-08-01 |  |  | 3
999 | Refactoring Goals

## Times
Work | Period | Date | Start | End | Hours | Goal | Goal Description
Got Data Validation Working | 3 | 2016-05-31 | 15:00 | 17:00 | 2:00 | 23 | Create Task Spreadsheet
Create Actual Update Report | 3 | 2016-06-01 | 8:30 | 12:30 | 4:00 | 23 | Create Task Spreadsheet
Organizing My Tasks | 4 | 2016-06-03 | 16:45 | 17:15 | 0:30 | 999 | Refactoring Goals
Messing around with JabRef | 4 | 2016-06-03 | 17:15 | 17:30 | 0:15 | 24 | Read all article Abstracts
Organizing Course Catalog | 4 | 2016-06-03 | 17:30 | 18:45 | 1:15 | 27 | Finish a complete class plan
Organizing Course Catalog | 4 | 2016-06-04 | 15:15 | 16:45 | 1:30 | 27 | Finish a complete class plan
Scanning Courses From Other Departments | 4 | 2016-06-04 | 19:30 | 21:30 | 2:00 | 27 | Finish a complete class plan
Polishing Update Database | 4 | 2016-06-05 | 12:00 | 14:30 | 2:30 | 25 | Add hours to Update Sheet
Polishing Update Database | 4 | 2016-06-05 | 15:30 | 17:00 | 1:30 | 25 | Add hours to Update Sheet

## Questions
Question | Answer | Date
Do I want to rework my course schedule skipping summer 2017? | No, I should assume I'll work during the summer and still take another semester after that. | 2016-06-01
Can I take non SYS classes to meet Course requirements? (e.g., CS 6316) | Yes, I can. The key is I can't take more than 3 hours under 5000 in Engineering. | 2016-06-01
Do I want any Sociology/Policy Classes for a CHS focus? | Yes, look through the catalog and see what interests me then talk to Gerber about it | 2016-06-01
What pace should I be going through these articles? | Just depends on where I am in my studies | 2016-06-01
How many articles should I cover in my survey presentation? | No specific number. Just cover what is interesting to me. | 2016-06-01

## Periods
Id | Start | End | Index | Period | Goal | Goal Description | Hours | Done | Index | Period | Goal | Description | Done | Index | Question
1 | 2016-05-11 | 2016-05-18 | -11 | 4 | 25 | Add hours to Update Sheet | 4:00 | TRUE | -13 | 5 | 14 | Reinforcement Learning an Introduction |  | -1
2 | 2016-05-18 | 2016-05-25 | -10 | 4 | 26 | Account for Conferences In Pub Plan | 0:00 | FALSE | -12 | 5 | 24 | Read all article Abstracts |  | -2
3 | 2016-05-25 | 2016-06-01 | -9 | 4 | 27 | Finish a complete class plan | 4:45 | FALSE | -14 | 5 | 13 | Introduction to Statistical Learning Chp 2 |  | -3
4 | 2016-06-01 | 2016-06-08 | -14 | 4 | 13 | Introduction to Statistical Learning Chp 2 | 0:00 | FALSE | -9 | 5 | 27 | Finish a complete class plan |  | -4
5 | 2016-06-08 | 2016-06-15 | -12 | 4 | 24 | Read all article Abstracts | 0:15 | FALSE | -11 | 5 |  |  |  | -5
|  |  | -13 | 4 | 14 | Reinforcement Learning an Introduction | 0:00 | FALSE | -10 | 5 | 26 | Account for Conferences In Pub Plan |  | -6
|  |  | -15 | 4 |  |  |  |  | -16 | 5 |  |  |  | -7
|  |  | -16 | 4 |  |  |  |  | -15 | 5 |  |  |  | -8
|  |  | -17 | 4 |  |  |  |  | -8 | 5 |  |  |  | -9
|  |  | -18 | 4 |  |  |  |  | -1 | 5 |  |  |  | -10
|  |  | -19 | 4 |  |  |  |  | -2 | 5
|  |  | -20 | 4 |  |  |  |  | -3 | 5
|  |  | -8 | 4 |  |  |  |  | -4 | 5
|  |  | -7 | 4 |  |  |  |  | -5 | 5
|  |  | -6 | 4 |  |  |  |  | -6 | 5
|  |  | -5 | 4 |  |  |  |  | -7 | 5
|  |  | -4 | 4 |  |  |  |  | -17 | 5
|  |  | -3 | 4 |  |  |  |  | -18 | 5
|  |  | -2 | 4 |  |  |  |  | -19 | 5
|  |  | -1 | 4 |  |  |  |  | -20 | 5
Formulas:
End = Periods[[#This Row],[Start]] + (7)

## Update
Mark Rucker |  |  |  | 2016-06-08
Last Week's Tasks | Time | Done | This Week Tasks
Add hours to Update Sheet | 4:00 | TRUE | Reinforcement Learning an Introduction
Account for Conferences In Pub Plan | 0:00 | FALSE | Read all article Abstracts
Finish a complete class plan | 4:45 | FALSE | Introduction to Statistical Learning Chp 2
Introduction to Statistical Learning Chp 2 | 0:00 | FALSE | Finish a complete class plan
Read all article Abstracts | 0:15 | FALSE
Reinforcement Learning an Introduction | 0:00 | FALSE | Account for Conferences In Pub Plan
Questions/Issues