## Goals
Id | Description | Comments | Due | Started | Finished | Current Period: 7
1 | Install JabRef on my personal machine |  | 2016-05-18 | 2 | 2
2 | Regain access to my UVA online account |  | 2016-05-18 | 2 | 2
3 | Get set up in my campus office |  | 2016-05-18 | 2 | 2
4 | Clone literature repository |  | 2016-05-19 | 2 | 2
5 | Set up my PTL private repository |  | 2016-05-19 | 2 | 2
6 | Write my first weekly update to my repository |  | 2016-05-19 | 2 | 2
8 | Read Prof. Gerber's thoughts |  | 2016-05-25 | 2 | 3
10 | Create curriculum plan |  | 2016-06-01 | 2 | 3
11 | Create publication plan |  | 2016-06-01 | 2 | 3
12 | Create thesis plan |  | 2016-06-01 | 2 | 3
9 | Connect to campus wifi |  | 2016-05-25 | 3 | 3
7 | Create Linux instance on AWS with R installed |  | 2016-05-25 | 3 | 3
23 | Create task spreadsheet |  | 2016-06-01 | 3 | 3
15 | Determine pace for article survey |  | 2016-06-01 | 3 | 3
13 | Introduction to Statistical Learning Chp 2 |  | 2016-06-08 | 3 | 4
25 | Add hours to update sheet |  | 2016-06-08 | 4 | 4
26 | Account for conferences in pub plan |  | 2016-06-08 | 4 | 4
27 | Finish first year class plan |  | 2016-06-08 | 4 | 5
18 | Send Jayne my TA preferences |  | 2016-06-17 | 5 | 5
32 | Uploading Open Source Data Library |  |  | 5 | 5
30 | Introduction to Statistical Learning |  |  | 2 | 7
14 | Reinforcement Learning an Introduction |  |  | 3 | 7
24 | Determine Research Interests |  |  | 3
29 | Integrate into UVA System |  |  | 4
33 | Read articles about research interests |  |  | 8
16 | Present a survey of my summer reading |  | 2016-07-26
22 | Research journals and submission criteria |  | 2016-08-01
28 | Register for classes |  | 2016-08-03
19 | Get campus ID card |  | 2016-08-04
17 | Fill out my vaccine medical form | Dr. Matt Hipke | 2016-08-05
27 | Sign up for Health Insurance |  | 2016-08-05
0 | Miscellaneous
Note on B30: Author: ID Cards To receive your University I.D. card you will need to go to the University I.D. Card Office, Observatory Hill Dining Hall between the hours of 8:30 a.m. and 4:30 p.m. after completion of your registration. For information regarding the University ID Card Office visit http://www.virginia.edu/idoffice/. Please remember to bring with you a valid state or government issued picture identification card (either your U.S. driver’s license, passport or U.S. military ID) in order to pick up your University ID. You will need your UVA email account first.
Note on B32: Author: ll students are required to have health insurance. Once you arrive on Grounds, and have picked up your ID card, you will be able to sign up for health insurance through the University sponsored health plan. If health insurance subsidy is included in your Financial Aid package, please go tohttp://www.aetnastudenthealth.com/stu_conn/student_connection.aspx?groupID=812806 to complete the Aetna Health Plan enrollment. This initial enrollment will cover the summer, through mid-August. You will need to pay for the insurance, and then request reimbursement from the department, because of your summer start date. You will register again for a full year in August, and will need documentation of your immunizations at that time.

## Times
Work | Period | Date | Start | End | Hours | Goal | Goal Description
Got data validation working | 3 | 2016-05-31 | 15:00 | 17:00 | 2:00 | 23 | Create task spreadsheet
Create actual update report | 3 | 2016-06-01 | 8:30 | 12:30 | 4:00 | 23 | Create task spreadsheet
Organizing goals | 4 | 2016-06-03 | 16:45 | 17:15 | 0:30 |  | Miscellaneous
Messing around with JabRef | 4 | 2016-06-03 | 17:15 | 17:30 | 0:15 | 24 | Determine Research Interests
Organizing course catalog | 4 | 2016-06-03 | 17:30 | 18:45 | 1:15 | 27 | Finish first year class plan
Organizing course catalog | 4 | 2016-06-04 | 15:15 | 16:45 | 1:30 | 27 | Finish first year class plan
Scanning courses from other departments | 4 | 2016-06-04 | 19:30 | 21:30 | 2:00 | 27 | Finish first year class plan
Polishing update database | 4 | 2016-06-05 | 12:00 | 14:30 | 2:30 | 25 | Add hours to update sheet
Polishing update database | 4 | 2016-06-05 | 15:30 | 17:15 | 1:45 | 25 | Add hours to update sheet
Shopping for a new laptop | 4 | 2016-06-05 | 18:30 | 19:45 | 1:15 | 29 | Integrate into UVA System
Finishing R labs for chapter 2 | 4 | 2016-06-05 | 20:15 | 20:45 | 0:30 | 13 | Introduction to Statistical Learning Chp 2
Reading Abstracts | 4 | 2016-06-06 | 19:00 | 20:15 | 1:15 | 24 | Determine Research Interests
Going through Jayne's Emails | 4 | 2015-06-06 | 20:15 | 21:15 | 1:00 | 29 | Integrate into UVA System
Playing with JabRef | 4 | 2016-06-07 | 13:00 | 15:15 | 2:15 | 24 | Determine Research Interests
Reviewing Course Listings Again | 4 | 2016-06-08 | 13:00 | 14:30 | 1:30 | 27 | Finish first year class plan
Write Jayne about my GTA classes | 5 | 2016-06-08 | 18:00 | 18:30 | 0:30 | 18 | Send Jayne my TA preferences
Made changes suggested by Gerber today | 5 | 2016-06-08 | 18:30 | 19:15 | 0:45 | 27 | Finish first year class plan
Reading Reinforcemet Learning | 5 | 2016-06-10 | 15:30 | 16:00 | 0:30 | 14 | Reinforcement Learning an Introduction
Reading Reinforcemet Learning | 5 | 2016-06-10 | 18:00 | 19:30 | 1:30 | 14 | Reinforcement Learning an Introduction
Reading Reinforcemet Learning | 5 | 2016-06-11 | 10:00 | 12:30 | 2:30 | 14 | Reinforcement Learning an Introduction
Organizing Updates | 5 | 2016-06-11 | 12:30 | 12:45 | 0:15 |  | Miscellaneous
Reading Reinforcemet Learning | 5 | 2016-06-11 | 19:00 | 20:15 | 1:15 | 14 | Reinforcement Learning an Introduction
Uploading Open Source Data Library | 5 | 2016-06-12 | 13:00 | 19:00 | 6:00 | 32 | Uploading Open Source Data Library
Uploading Open Source Data Library | 5 | 2016-06-13 | 14:00 | 19:00 | 5:00 | 32 | Uploading Open Source Data Library
Uploading Open Source Data Library | 5 | 2016-06-14 | 14:00 | 18:30 | 4:30 | 32 | Uploading Open Source Data Library
Reading Reinforcemet Learning | 5 | 2016-06-15 | 12:30 | 14:30 | 2:00 | 14 | Reinforcement Learning an Introduction
Reading Reinforcemet Learning | 6 | 2016-06-15 | 19:00 | 19:45 | 0:45 | 14 | Reinforcement Learning an Introduction
Reading Reinforcemet Learning | 6 | 2016-06-16 | 14:15 | 15:30 | 1:15 | 14 | Reinforcement Learning an Introduction
Writing email asking about IP | 6 | 2016-06-17 | 15:30 | 16:30 | 1:00 | 29 | Integrate into UVA System
Reading Reinforcemet Learning | 6 | 2016-06-18 | 11:15 | 12:45 | 1:30 | 14 | Reinforcement Learning an Introduction
Reading Reinforcemet Learning | 6 | 2016-06-19 | 19:00 | 21:00 | 2:00 | 14 | Reinforcement Learning an Introduction
Reading Reinforcemet Learning | 6 | 2016-06-20 | 13:45 | 14:45 | 1:00 | 14 | Reinforcement Learning an Introduction
Reading Reinforcemet Learning | 6 | 2016-06-20 | 20:45 | 22:30 | 1:45 | 14 | Reinforcement Learning an Introduction
Attending weekly lab meeting | 6 | 2016-06-21 | 12:00 | 13:30 | 1:30 | 29 | Integrate into UVA System
Reading Reinforcemet Learning | 6 | 2016-06-21 | 16:45 | 18:00 | 1:15 | 14 | Reinforcement Learning an Introduction
Reading Reinforcemet Learning | 6 | 2016-06-21 | 21:15 | 22:15 | 1:00 | 14 | Reinforcement Learning an Introduction
Reading Reinforcemet Learning | 6 | 2016-06-22 | 14:00 | 16:00 | 2:00 | 14 | Reinforcement Learning an Introduction
Reading Articles | 7 | 2016-06-23 | 16:15 | 17:15 | 1:00 | 24 | Determine Research Interests
Reading Articles | 7 | 2016-06-24 | 13:00 | 14:45 | 1:45 | 24 | Determine Research Interests
Reading Articles | 7 | 2016-06-24 | 16:45 | 18:00 | 1:15 | 24 | Determine Research Interests
Reading Articles | 7 | 2016-06-25 | 12:15 | 14:45 | 2:30 | 24 | Determine Research Interests
Reading Articles | 7 | 2016-06-25 | 15:30 | 17:30 | 2:00 | 24 | Determine Research Interests
Reading Articles | 7 | 2016-06-26 | 13:00 | 14:00 | 1:00 | 24 | Determine Research Interests
Reading Articles | 7 | 2016-06-26 | 14:30 | 15:30 | 1:00 | 24 | Determine Research Interests
Reading Articles | 7 | 2016-06-26 | 20:15 | 21:15 | 1:00 | 24 | Determine Research Interests
Filling out Vacine Paperwork | 7 | 2016-06-27 | 13:15 | 14:00 | 0:45 | 29 | Integrate into UVA System
Setting up Sensus with protocol | 7 | 2016-06-27 | 14:00 | 14:15 | 0:15 | 29 | Integrate into UVA System
Follow up email to Josh about IP Protocol | 7 | 2016-06-27 | 14:15 | 15:00 | 0:45 | 29 | Integrate into UVA System
Coordinating move into long-term lease | 7 | 2016-06-27 | 15:00 | 15:15 | 0:15 | 29 | Integrate into UVA System
Follow up email to Josh about IP Protocol | 7 | 2016-06-27 | 15:15 | 15:30 | 0:15 | 29 | Integrate into UVA System
Weekly lab meeting with team | 7 | 2016-06-28 | 14:00 | 15:15 | 1:15 | 24 | Determine Research Interests
Meeting with Prof. Mondschein | 7 | 2016-06-28 | 16:00 | 17:00 | 1:00 | 24 | Determine Research Interests
Reading Articles | 7 | 2016-06-29 | 14:00 | 15:00 | 1:00 | 24 | Determine Research Interests
Update With Prof. Gerber | 7 | 2016-06-29 | 15:00 | 16:00 | 1:00 | 29 | Integrate into UVA System
Hiking with Gerber's Team | 8 | 2016-06-30 | 7:30 | 13:15 | 5:45 | 29 | Integrate into UVA System

## Questions
Question | Answer
Can we look at how physical infrastructure impacts a community for inspiration? | A professor of architect just asked Gerber about this today
How important are Markov Decision Processes to Systems research? | in PDF
Is Machine Learning being used to create models of systems? I guess it'd be something like optimal control? | in PDF
Does Systems research include systems that make decisions? E.g., a system of Reinforcement Learners? | in PDF
Do UVA courses cover self-correcting systems? I didn't see it in the catalog. It seems important to control/learning. | in PDF
Do you know of any ongoing CHS experiments? I'm struggling to imagine experiements for something as abstract as CHS. | in PDF
What pace should I be going through these articles? | Just depends on where I am in my studies
I have a wedding in OKC on January 14th? | No problem
How many articles should I cover in my survey presentation? | No specific number. Just cover what is interesting to me.
Do I want to rework my course schedule skipping summer 2017? | No, I should assume I'll work during the summer and still take another semester after that.
How have HHS systems been modeled? | Not that Gerber knows of
What classes am I "qualified" to GTA? | SYS 2001, CS *, APMA
Can we design a CHS conceptual framework that works in all situations? | That's the hope
Can we model ubiquitious computing's impact on a community without individuals? | That's the question
Can we model ubiquitious computing's impact on any or just one at a time? | That's the question
Can I use my own branch in literature? | Yes
I'm interested in machine learning but does that help me model? | Yes I need to learn it
Can I take non SYS classes to meet Course requirements? (e.g., CS 6316) | Yes, I can. The key is I can't take more than 3 hours under 5000 in Engineering.
Do I want any Sociology/Policy Classes for a CHS focus? | Yes, look through the catalog and see what interests me then talk to Gerber about it
How does the University handle source code I write as a student? | In touch with Josh. Seems straight forward though from http://uvapolicy.virginia.edu/policy/RES-001#Sponsors
Modeling UbiComp social systems? | Models are weak in research because it is very hard to show how well they fit reality
Unsupervised Google Result Classifier? | The more abstract research question: Determining objectives through observation

## Periods
Id | Start | End | Hours | Index | Period | Show | Goal | Goal Description | Hours | Done | Index | Period | Show | Goal | Description | Index | Question
1 | 2016-05-11 | 2016-05-18 | 0 | -10 | 8 | TRUE | 24 | Determine Research Interests | 0 |  | -10 | 9 | TRUE | 24 | Determine Research Interests | -1
2 | 2016-05-18 | 2016-05-25 | 0 | -9 | 8 | TRUE | 29 | Integrate into UVA System | 0.23958 |  | -9 | 9 | TRUE | 29 | Integrate into UVA System | -2
3 | 2016-05-25 | 2016-06-01 | 0.25 | -8 | 8 | TRUE | 33 | Read articles about research interests | 0 |  | -8 | 9 | TRUE | 33 | Read articles about research interests | -3
4 | 2016-06-01 | 2016-06-08 | 0.72917 | -20 | 8 | FALSE |  |  |  |  | -20 | 9 | FALSE |  |  | -4
5 | 2016-06-08 | 2016-06-15 | 1899-12-31 00:45 | -19 | 8 | FALSE |  |  |  |  | -19 | 9 | FALSE |  |  | -5
6 | 2016-06-15 | 2016-06-22 | 0.625 | -18 | 8 | FALSE |  |  |  |  | -18 | 9 | FALSE |  |  | -6
7 | 2016-06-22 | 2016-06-29 | 0.75 | -17 | 8 | FALSE |  |  |  |  | -17 | 9 | FALSE |  |  | -7
8 | 2016-06-29 | 2016-07-06 | 0.23958 | -16 | 8 | FALSE |  |  |  |  | -16 | 9 | FALSE |  |  | -8
|  |  |  | -15 | 8 | FALSE |  |  |  |  | -15 | 9 | FALSE |  |  | -9
|  |  |  | -14 | 8 | FALSE |  |  |  |  | -14 | 9 | FALSE |  |  | -10
|  |  |  | -13 | 8 | FALSE |  |  |  |  | -13 | 9 | FALSE |  |  | -11
|  |  |  | -12 | 8 | FALSE |  |  |  |  | -12 | 9 | FALSE
|  |  |  | -11 | 8 | FALSE |  |  |  |  | -11 | 9 | FALSE
|  |  |  | -7 | 8 | FALSE |  |  |  |  | -7 | 9 | FALSE
|  |  |  | -6 | 8 | FALSE |  |  |  |  | -6 | 9 | FALSE
|  |  |  | -5 | 8 | FALSE |  |  |  |  | -5 | 9 | FALSE
|  |  |  | -4 | 8 | FALSE |  |  |  |  | -4 | 9 | FALSE
|  |  |  | -3 | 8 | FALSE |  |  |  |  | -3 | 9 | FALSE
|  |  |  | -2 | 8 | FALSE |  |  |  |  | -2 | 9 | FALSE
|  |  |  | -1 | 8 | FALSE |  |  |  |  | -1 | 9 | FALSE
Formulas:
End = Periods[[#This Row],[Start]] + (7)
Hours = SUM((Times[Period] = Periods[[#This Row],[Id]]) * Times[Hours])
Hours = IF(LastWeekTasks[[#This Row],[Goal]] = "", "", SUM((Times[Period] = LastWeekTasks[[#This Row],[Period]]) * (Times[Goal] = LastWeekTasks[[#This Row],[Goal]]) * (Times[Hours])))

## Update
Mark Rucker |  |  |  | 2016-06-29
Last Week's Tasks | Time | Done | This Week Tasks
Determine Research Interests | 0 |  | Determine Research Interests
Integrate into UVA System | 0.23958 |  | Integrate into UVA System
Read articles about research interests | 0 |  | Read articles about research interests
Questions/Issues
Formulas:
Time = LastWeekTasks[Hours]